## ورقة1
Type | Current Situation / Considerations | Proposed Solution / Benefits | Feasibility Result
Technical | Prerequisites and credit hours are checked manually; scheduling conflicts are found late; no real-time seat information. | Web system with a rules engine (prerequisites, credit limits, schedule conflicts) on PostgreSQL/MySQL; scalable architecture for peak registration week. | ✅ Technically feasible
Operational | Manual review slows registration; long queues at student affairs; academic advisors overloaded with paper checking. | Self-service registration; advisors move to academic mentoring; basic training on override requests. | ✅ Operationally feasible
Economic | Cost of software, hardware, training, and maintenance (about 200,000 EGP one-time + 40,000 EGP per year). | Saves staff time, paper, and error-correction costs (about 180,000 EGP per year); payback in about 1.4 years. | ✅ Cost-effective
Legal | Student records, grades, and GPA data are personal data. | Role-based access for students, advisors, and admins; compliance with the university bylaws and data-protection rules. | ✅ Legally feasible
Schedule | Registration weeks are fixed; the system must be ready and available 24/7 during the registration period. | Estimated timeline of about 5 months (requirements, design, development, testing, deployment). | ✅ Achievable timeline

## ورقة2
Cost–Benefit Analysis Table for the Course Registration System (CRS):
Cost–Benefit Analysis – Course Registration System (CRS)
Category | Description | Estimated Cost | Benefits | Estimated Value (per year)
Software | Development (in-house): rules engine (prerequisites, credit limits, schedule check), registration portal, reports | 160,000 EGP | Prevents registration without prerequisites or with wrong credit hours. | 50,000 EGP savings in registration errors
Hardware | Server/cloud hosting setup, backup storage | 25,000 EGP | Peak-load capacity and 24/7 availability during registration week. | 90,000 EGP saved in staff workload
Training | Basic training for advisors and administrators on override requests and registration management | 15,000 EGP | Smooth adoption of the system. | Higher productivity (intangible, not counted)
Maintenance | Annual updates, bug fixes, hosting, support | 40,000 EGP annually | Keeps the rules engine aligned with the university bylaws. | Avoids downtime (intangible, not counted)
Administration | Current manual process (paper checking, printing, correction forms) | 40,000 EGP annually | Physical queues and paper checking eliminated. | 40,000 EGP saved
User Experience | Days spent on registration; no real-time seat information | – | Transparent, fast self-service registration without scheduling conflicts | Intangible but high value
## Summary
Total Estimated Costs (first year): 240,000 EGP (200,000 one-time + 40,000 operating)
Total Estimated Annual Benefits/Savings: 180,000 EGP
Payback Period: about 1.4 years (200,000 ÷ 140,000 net annual benefit)
Conclusion: The Course Registration System is economically feasible, with clear cost savings and long-term value.