Methodology

Project Methodology–Course Registration System Project

Selected Methodology: - Agile Development: the system is built in short sprints, and each sprint delivers a working module.

Reasons: - Advisor Feedback: credit limits and student-status rules are refined with feedback from academic advisors. - Modular System: Student Management, Course Management, Rules Engine, and Reports Panel can be delivered one by one. - Team Communication: a team of four members working face to face.

Sprint Plan (Implementation phase, 3 sprints of 14 days): - Sprint 1: Student Management and Course Management. - Sprint 2: Rules Engine: prerequisite verification, credit limits by GPA and student status, and schedule check. - Sprint 3: Reports Panel, load testing for registration week, and advisor training.

Case Study

Case Study–Course Registration System

Background: The university relies on manual review of prerequisites and manual calculation of minimum and maximum credit hours during each semester registration period.

Problems Identified: - Human Errors: manual record checking causes prerequisite and credit-hour errors. - Long Queues: students crowd student affairs at the start of each semester. - No Seat Information: available seats cannot be seen in real time. - Scheduling Conflicts: conflicts between lectures or final exams are found late. - Administrative Burden: advisors spend registration week on manual paper-checking.

Project Objectives: - Prerequisite Verification: prevent registration in a course without its prerequisite. - Credit Limits: apply minimum and maximum credit hours by GPA and student status. - Schedule Check: detect conflicts before the schedule is confirmed. - Real-Time Seats: show available seats for each section. - Reports: give the administration enrollment reports per course.

Development Plan (SDLC): - Planning: goals, feasibility, and resources. - Analysis: requirements from students, advisors, and administrators. - Design: data model, rules engine, and interface. - Implementation: build, test, deploy, and train advisors.

Question: Which SDLC methodology is most suitable for this project? Answer: Agile Development. The rules engine is refined with advisor feedback, and working modules are delivered in sprints before the registration week.

Time Estimation

| Phase | Percentage | Estimated Time (days) |
| --- | --- | --- |
| Planning | 15% | 21 |
| Analysis | 20% | 28 |
| Design | 35% | 49 |
| Implementation | 30% | 42 |
| Total | 100% | 140 (20 weeks) |

- Planning Time: 21 days, the minimum duration of the planning activities (see PERT Chart).

- Total Project Time: 21 ÷ 0.15 = 140 days.

PERT Chart

| Activity | Description | Predecessors | Duration (days) |
| --- | --- | --- | --- |
| A | System Request | - | 3 |
| B | Feasibility Study | - | 7 |
| C | Methodology | B | 3 |
| D | Time Estimation | A, C | 2 |
| E | Task Identification | C | 3 |
| F | PERT Chart | C | 7 |
| G | Gantt Chart | D, E, F | 4 |

- Critical Path: B, C, F, G.

- Minimum Duration: 7 + 3 + 7 + 4 = 21 days.

Gantt Chart

- Critical Path: B, C, F, G.

- Minimum Duration: 21 days.